## PT Worksheet
Client | CLIENT NAME
Contract Start Date | 2014-09-03 |  |  |  | Contract Renew Date | 2015-03-04
Week # | Target Completion Date | Customized Completion Date | Administration | Stage 1 Candid Look | Stage 2 Future Map | Stage 3 Legal Options | Stage 4 Potential Benefits | Stage 5 Document the Wonder | Stage 6 Begin Transition | Stage 7 Funding | Stage 8 Review & Renew
1 | 2014-09-10 | 2014-09-10 | 1. Turn in contract 2. Obtain Online ID
2 | 2014-09-17 | 2014-09-17 | Obtain signed consent to access online system | Stage 1 Complete - client enters online | Begin Stage 2
3 | 2014-09-24 | 2014-09-24 |  |  | Complete Stage 2 (if necessary, schedule t/c or webinar to assist) |  | Begin Stage 4 - Abilities
4 | 2014-10-01 | 2014-10-01 |  |  |  | 1. Begin Stage 3 Wkst 2. Schedule Atty Mtg | Complete Stage 4 - Abilities |  |  | Begin Stage 7
5 | 2014-10-08 | 2014-10-08
6 | 2014-10-15 | 2014-10-15 |  |  |  | Complete Stage 3 (if necessary schedule T/C or Webinar to assist)
7 | 2014-10-22 | 2014-10-22 |  |  |  | Prepare Atty Intake Form - Send to Atty w/ Stage 1, 3, 4 & other pertinent info
8 | 2014-10-29 | 2014-10-29 |  |  |  | ATTORNEY MEETING
9 | 2014-11-05 | 2014-11-05
10 | 2014-11-12 | 2014-11-12 | [5 empty] | Begin Stage 5
11 | 2014-11-19 | 2014-11-19
12 | 2014-11-26 | 2014-11-26 |  |  |  | Legal Docs Complete Atty to Begin Re-titling, if necessary |  |  |  | Complete Stage 7 Plan
13 | 2014-12-03 | 2014-12-03 |  |  | Complete Stage 3
14 | 2014-12-10 | 2014-12-10
15 | 2014-12-17 | 2014-12-17
16 | 2014-12-24 | 2014-12-24 | [6 empty] | Begin Stage 6
17 | 2014-12-31 | 2014-12-31
18 | 2015-01-07 | 2015-01-07
19 | 2015-01-14 | 2015-01-14
20 | 2015-01-21 | 2015-01-21 | [7 empty] | Implement Stage 7 Plan
21 | 2015-01-28 | 2015-01-28
22 | 2015-02-04 | 2015-02-04 | [8 empty] | Begin Stage 8
23 | 2015-02-11 | 2015-02-11
24 | 2015-02-18 | 2015-02-18
25 | 2015-02-25 | 2015-02-25
26 | 2015-03-04 | 2015-03-04 | [6 empty] | Complete Stage 6 |  | Complete Stage 8
Formulas:
Target Completion Date = [Target Completion Date, row above]+7
Customized Completion Date = [Target Completion Date]

## Client Worksheet
CLIENT NAME
Contract Signed
2014-09-03
Recommended Action | GOAL START Date | GOAL COMPLETION Date | ACTUAL COMPLETION Date | Plus | Plus
Stage 1: Take a Candid Look
Look honestly and comprehensively at your loved one’s future care needs, in light of your own future needs and those of other family members. | 2014-09-10 | 2014-09-10 |  | 7 | 7
Stage 2: Create the Future Map
Identify the options and create a plan to protect your entire family’s future in light of your family member’s special needs. | 2014-09-17 | 2014-10-01 |  | 14 | 28
Stage 3: Filter the Legal Options
Evaluate estate solutions, focusing on the various options available through professional legal resources. Implement the steps to take advantage of your decisions.
Phase 1 - Prepare for Initial Attorney Meeting | 2014-10-01 | 2014-10-15 |  | 28 | 42
Phase 2 - Attorney Meeting | 2014-10-29 | 2014-10-29 |  | 56 | 56
Phase 3 - Documents completed by Attorney and Signed by Client | 2014-11-26 | 2014-12-24 |  | 84 | 112
Stage 4: Capture Potential Benefits
Identify and apply for supplemental programs to enhance and supplement the Future Care Plan you have created for your loved one. | 2014-09-24 | 2014-10-01 |  | 21 | 28
Stage 5: Document the Wonder
Chronicle and treasure your loved one’s special story and gifts so that others can carry forward in building your family member’s abilities and self-esteem. | 2014-11-12 | 2015-02-25 |  | 70 | 173
Stage 6: Begin the Transition
Identify and evaluate the future residential, employment, and recreation options for your special needs family member. | 2014-12-24 | 2015-02-25 |  | 112 | 173
Stage 7: Fund the Future
Utilize financial solutions to complement the Future Care Plan designed for your family member’s future.
Phase 1 - Prepare Plan | 2014-10-01 | 2014-11-26 |  | 28 | 84
Phase 2 - Implement Plan | 2014-11-26 | 2015-01-21 |  | 84 | 138
Stage 8: Review and Renew
Review annually your future Care Plan to accommodate and address life’s inevitable changes. | 2015-02-04 | 2015-02-25 |  | 154 | 175